**Vet Pet (Health Insurance**

**and Patient Management**

**System) Weekly Status**

**November 4, 2018**

**CSCI-P465/565 (Software Engineering I)**

**Status for week ending Nov 4, 18**

**Elements of Weekly Status:**



**Project Function, Deliverable, Component Name**

|  |  |  |  |
| --- | --- | --- | --- |
| Activities | People | Time(optional) | Details |
| Search doctors using filters, Rate Doctors and Chat API | Jainendra Kumar | Oct 30, 2018, | Jainendra modified the search doctor feature by adding filter search.  Also, started with the implementation of chat feature in the system. |
| Weekly Status  Report | Amey Tarfe | Nov 4,2018 | Amey Tarfe was responsible for the weekly status report, recording this week’s status and man-hours worked this week. |
| UI for Homepage and Login page | Christian Gonzalez | Oct 31,2018 | Christian worked on improving the interface of the Login and registration page of the system. |



|  |  |  |  |
| --- | --- | --- | --- |
| Search Insurance  Providers module | Xinran Dai | Oct 30, 2018 | Xinran enhanced the database tables of Search Insurance Providers module in which the users will be able to search for insurance providers by their names or by package details. |
| Homepage UI | Amey Tarfe | Oct 31, 2018 | Amey implemented some additions and modifications on the homepage of the webite. |

**Responsible Person**

Requirements Development - NA (not started) Design



* Search Insurance Providers module: Xinran Dai (8 hour)
* Install packages and setting up environment: Xinran Dai (3 hour)

Implementation

- Registration and Login Page UI: Christian Gonzalez (14 hour)

* Rate and Search Doctors using filters: Jainendra Kumar (9 hour)
* Chat API: Jainendra Kuma (2 hour)
* Designing the homepage (UI): Amey Tarfe (4 hour)

Test - NA (not started)

Delivery - NA (not started)

Project Management

* Meeting planning and time schedule coordination: Jainendra Kumar (0.5 hour)

Change Control

* Weekly Status Report: Amey Tarfe (1 hour)

**Estimated Component Percent Complete**

For each identified component, indicate the estimated completion percentage

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Project Function,**  **Deliverable, or** **Component** | **Responsible**  **Person** | **Man-Hours Worked this Week** | | | | | | | | **Estimated**  **Component**  **Percent Complete** |
| **Name** |  | **Proj Plan** | **Req Dev** | **Design** | **Impl** | **Test** | **Deliv** | **Proj**  **Mgmt** | **Chng**  **Crl** |  |
| Homepage UI | Amey Tarfe |  |  |  | 4hr |  |  |  |  | 75% |
| Registration and Login page UI | Christian Gonzalez |  | 1hr | 2hr | 9hr | 2hr |  |  |  | 75% |
| Search doctors (Filters, Rate doctors) | Jainendra Kumar |  |  |  | 6hr | 3hr |  |  |  | 75% |
| Chat API | Jainendra Kumar |  |  |  | 2 hr |  |  |  |  | 30% |
| Search Insurance providers and plans (Database modifications) | Xinran Dai |  |  |  | 6hr | 2hr |  |  |  | 100% |
| Setting up environment and package instalment | Xinran Dai |  |  |  | 3hr |  |  |  |  | 100% |
| Weekly Status Report | Amey Tarfe |  |  |  |  |  |  | 1hr |  | 100% |

**Page Author/Creator:** [Adeel Bhutta](http://homes.soic.indiana.edu/aabhutta/)

**Last Modified:** 11/4/2018