**Vet Pet (Health Insurance**

**and Patient Management**

**System) Weekly Status**

**December 2, 2018**

**CSCI-P465/565 (Software Engineering I)**

**Status for week ending Dec 2, 18**

**Elements of Weekly Status:**



**Project Function, Deliverable, Component Name**

|  |  |  |  |
| --- | --- | --- | --- |
| Activities | People | Time(optional) | Details |
| Hospital locator,  Doctor view | Jainendra Kumar | Nov 23, 2018, | Jainendra modified the search doctor feature by adding filter search.  Also, added a hospital locator. |
| Weekly Status  Report | Amey Tarfe | Dec 2,2018 | Amey Tarfe was responsible for the weekly status report, recording this week’s status and man-hours worked this week. |
| Chat feature | Christian Gonzalez | Nov 25,2018 | Christian worked on the chat feature. |



|  |  |  |  |
| --- | --- | --- | --- |
| Search Insurance  Providers module | Xinran Dai | Nov 19, 2018 | Xinran enhanced the database tables of Search Insurance Providers module in which the users will be able to search for insurance providers by their names or by package details. |
| Insurance provider UI | Amey Tarfe , Jainendra Kumar | Nov 19, 2018 | Amey and Jainendra implemented some additions and modifications on the insurance provider page of the website. |
| Homepage UI | Amey Tarfe , Jainendra Kumar | Nov 19, 2018 | Amey and Jainendra implemented some additions and modifications on the homepage of the website. |

**Responsible Person**

Requirements Development - Design



* Fixing the UI for each of the pages: Amey Tarfe (6 hours)
* UI for Search doctors: Jainendra Kumar (9 hours)
* UI for homepage: Jainendra Kumar (2 hours)
* UI for insurance providers: Jainendra Kumar (2 hours)
* Search provider UI: Christian Gonzalez (8 hours)

Implementation

- Chat feature: Christian Gonzalez (24 hours)

* Hospital locator: Jainendra Kumar (2 hours)
* Homepage images: Jainendra Kumar (3 hour)
* Database for doctors: Jainendra Kumar (2 hours)
* Provider database: Jainendra Kumar (5 hours)
* Insurance table: Jainendra Kumar (2 hour)
* Insurance provider UI: Amey Tarfe (12 hour)
* Implementing the homepage (UI): Amey Tarfe (12 hour)
* Filterable table search: Christian Gonzalez (18 hours)
* Insurance Selection: Xinran Dai (9 hours)
* Payment database: Xinran Dai (3 hours)
* Database: Xinran Dai (8 hours)
* Insurance provider view: Xinran Dai (2 hours)
* Patient profile: Xinran Dai (7.5 hours)
* Insurance plans: Xinran Dai (2 hours)

Test –

* Testing the UI elements: Amey Tarfe (5 hours)
* Fixed OAuth: Christian Gonzalez (8 hours)

Delivery – Deployment: Christian Gonzalez (3 hours)

Project Management

* Weekly Status Report: Amey Tarfe (0.5 hour)
* System Design, Test plan, User Manual: Amey Tarfe (4 hours)

Change Control



**Estimated Component Percent Complete**

For each identified component, indicate the estimated completion percentage

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Project Function,**  **Deliverable, or** **Component** | **Responsible**  **Person** | **Man-Hours Worked this Week** | | | | | | | | **Estimated**  **Component**  **Percent Complete** |
| **Name** |  | **Proj Plan** | **Req Dev** | **Design** | **Impl** | **Test** | **Deliv** | **Proj**  **Mgmt** | **Chng**  **Crl** |  |
| UI design for all of the pages. | Amey Tarfe |  |  | 6hr | 24hr | 5hr |  |  |  | 100% |
| UI design for all of the pages. | Jainendra Kumar |  |  | 13hr | 3 |  |  |  |  | 100% |
| Insurance provider UI | Christian Gonzalez |  |  | 8hr |  |  |  |  |  | 100% |
| Chat feature | Christian Gonzalez |  |  |  | 24hr |  |  |  |  | 90% |
| Filterable Search | Christian Gonzalez |  |  |  | 18hr |  |  |  |  | 100% |
| Fixed OAuth | Christian Gonzalez |  |  |  | 8hr |  |  |  |  | 10% |
| Database for doctors, insurance providers | Jainendra Kumar |  |  |  | 9hr |  |  |  |  | 100% |
| Patient profile | Xinran Dai |  |  |  | 7.5hr |  |  |  |  | 90% |
| Hospital locator | Jainendra Kumar |  |  |  | 2 hr |  |  |  |  | 100% |
| Insurance Selection | Xinran Dai |  |  |  | 9hr |  |  |  |  | 100% |
| Database for providers and payment | Xinran Dai |  |  |  | 11hr |  |  |  |  | 100% |
| Insurance provider view | Xinran Dai |  |  |  | 4 hr |  |  |  |  | 60% |
| Weekly Status Report, System Design, Test plan, Customer meeting minutes and User Manual | Amey Tarfe |  |  |  |  |  |  | 4.5hr |  | 100% |

**Page Author/Creator:**Amey Avinash Tarfe

**Last Modified:** 12/2/2018